## Tabelle1
Must Have (sprint backlog)					estimation in story points			finished
Document containing the user stories and roles:				list of roles: missing (-1)			0.1	finished		0.1
				user stories update			0.1	finished		0.1
Domain Model:		Do not use navigability arrows in domain models					0.1	finished		0.1

Class Administrator					0.5	finished		0.5

		Hint: introduce name for associations					0.1	finished		0.1

Stakeholders: (-1)		Missing: Developer, User, ...					0.1	finished		0.1

Update of existing documents:

			Domain model document not updated (-2)				0.3	finished		0.3

Sprint backlog items, task and their states:				Estimates missing (-2)			0.7	finished	effort in hours: 0,5 -1	0.7

Production classes and interfaces:			Package names: use small letters				0.3	finished		0.3

Working infrastructure with persistence:

			Using H2 in-memory database is recommended				3

Checkstyle report: (-4)		Many Checkstyle errors (set up IDE automatically fix them)					1	finished		1

Miscellaneous:		Errors in JavaDoc comment (-2)					0.5	finished		0.5

				total remaining	3

Remaining product backlog items

Nice to have

Bad name: User					0.5

As a administrator I want to add a resource to the system, so a user can book the resource				FindResourceTest		1

Junit tests, code coverage:					90% code coverage of the core layers (UI components excluded)					JUnit test classes for the application logic and persistence (not necessarily for the user interface)					Provide code for selected user stories of this sprint

			Bad coverage (-4)				3

As a user I want to get an overview of the resources, so I can decide which resource I want to reserve			TestClass	2	JPA: select resources		2

The Jdepend report (no cycles allowed; respect the Stable Dependency Principle and the Stable Abstractions Principle)					1		Stable structure in terms of Java packages respecting the SOLID design principles

working infrastructure: (-2)		UI: no progress

Update of existing documents:			User story document not updated (-2)

Production classes and interfaces:			UI: No progress (-2)

Working infrastructure with persistence:			When using MySQL: Add driver as Maven dependency

Junit tests, code coverage:			Unit test CreateResourceTest.create() fails (-2)

Provide the documentation of your software

As a user I want to get an overview of the availibility of a resource(time frames, when a resource is available) , so I can decide on which time frame I want to reserve the resource			JPA: Reservation	JPA: column reservation in table resource (foreign key)		2
As a user I want to see an overview of my reservation, so I can see my reservations			JPA: User	JPA: column reservation in table user (foreign key)				2

won‘t have

As a user I want to see an overview of my reservation, so I can cancel a reservation		UserInterface
As a user I want to log in to the system, so that I have acces to my reservations and to the resources		Class Controller method login, UserInterface
(As a administrator I want to delete a resource, so that no user can reserve the resource.)		Class Controller, method deleteResource	Class DeleteResource	DeleteResourceTest
(As a user I want to be able to decide on different dates and time frames, so that I can make a irregularly recurring reservation)
(As a user I want to decide if a recurring booking is daily, weekly or monthly, so that I don't have to book the same resource each time)

## Tabelle2
The Product Owner and team should collaborate about an hour per week on backlog refinement (aka “backlog grooming”) to convert large fuzzy requirements (“epics”) into more distinct user stories

If a PBI would take more than a quarter of a two-week Sprint, it’s probably too big.

Only a subset of these PBIs, the Sprint Backlog, are tackled by the team in a given Sprint. During Sprint Planning, and during the Sprint itself, the team discovers and tracks the Sprint Tasks necessary to accomplish each PBI in the Sprint Backlog.